## Summary
Project Sheet - Summary
| Project Name | SimPancake 3000 | Project Type | Alt-Ctrl & Video Game
| Start Date | 2019-05-15 | Target end date | 2019-06-15
| Days To go | 11 | Project Length (days) | 31
| That's | 64.52% | Of your fucking time used
Progress (All)
| Compleat | 14 | Incompleat | 14 | Total Jobs | 28 | Work in Progress | 1
| % | 50% | % | 50% | % | 100% | % | 3.571%
| Peak % | 50%
Todo
| Task / Todo |  |  |  | Task / Todo
| Not Stated | 9 | 45% |  | Not Stated | 4 | 20%
| WIP | 1 | 5% |  | WIP | 0 | 0%
| Testing | 0 | 0% |  | Testing | 0 | 0%
| Compleat | 10 | 50% |  | Compleat | 4 | 20%
| Removed | 0 | 0% |  | Removed | 0 | 0%
| Fixed | 0 | 0% |  | Fixed | 0 | 0%
| Total | 20 | 100% |  | Total | 20 | 40%
| Incompleat Task | 50% |  |  | Incompleat Task | 20%
| Compleat Task | 50% |  |  | Compleat Task | 20%
Progress Log | [5 empty] | Task Stats |  |  |  |  | Even move fucking task stats
[6 empty] | Task | % | Task Compleat | % | Completed / Add ratio | Avg tasks added Per day | Avg Tasks Comp per day | Actual % to now
# | Date | Task Count | Task Compleat | Incompleat tast | % | [8 empty] | Actual % in Week
0 | 2019-05-20 | 20 | 7 | 13 | 35% | 20 | 0% | 7 | 0% | 0.35 | 4 | 1.4 | 25% | 25%
1 | 2019-05-27 | 24 | 11 | 13 | 45.83% | 4 | -80% | 4 | -42.86% | 1 | 0.57143 | 0.57143 | 39.29% | 14.29%
2 | 2019-06-03 | 28 | 12 | 16 | 42.86% | 4 | 0% | 12 | 200% | 3 | 0.57143 | 1.7143 | 42.86% | 28.57%
3 | 2019-06-10 | 0 | 0 | 0 | #DIV/0! | -28 | -800% | 0 | -100% | 0 | -28 | 0 | 0% | -28.57%
4 | 2019-06-17 | 0 | 0 | 0 | #DIV/0! | 0 | -100% | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0% | 28.57%
Formulas:
SimPancake 3000 = DAYS([Alt-Ctrl & Video Game, row above],NOW())
Alt-Ctrl & Video Game = DAYS([Alt-Ctrl & Video Game, row above],[SimPancake 3000, row above])
Even move fucking task stats = IF(NOW()<[Project Name], [Task Stats]/DAYS(NOW(),C4), [Task Stats]/DAYS([Project Name],C4))
Even move fucking task stats = IF(NOW()<[Project Name], [Task Stats]/DAYS(NOW(),[Project Name, row above]), [Task Stats]/DAYS([Project Name],[Project Name, row above]))
Avg Tasks Comp per day = IF(NOW()<[Project Name], [Task Compleat]/DAYS(NOW(),C4), [Task Compleat]/DAYS([Project Name],C4))
Avg Tasks Comp per day = IF(NOW()<[Project Name], [Task Compleat]/DAYS(NOW(),[Project Name, row above]), [Task Compleat]/DAYS([Project Name],[Project Name, row above]))

## Todo (Game Main)
Project Sheet - Todo
ID | Task Name | Task Details | Status | Group | Sub Group | Notes
0 | Add Pan |  | C | MVP
1 | Add Pancakes |  | C | MVP
2 | Add Jug |  | C | MVP
3 | Add input Handler | this should deal with both mouse/keyboard inputs and serial | C | Main Comp |  | We could use the mosue to controle the things if there is no serial
4 | Add Level Controller |  | - | Main Comp
5 | Add Game Manager |  | - | Main Comp
6 | Add Level Manager |  | - | Main Comp
7 | Add Static Game class |  | - | Main Comp
8 | Add Save/Load |  | - | Main Comp
9 | Add High Score |  | - | Online
10 | Add Fire Alarm |  | - | MVP
11 | Add Nob Hobs |  | C | MVP
12 | Add Pan detect hobs |  | C | MVP
13 | Add Fire |  | - | MVP
14 | Add Batter |  | C | MVP
15 | Add Hob Fire |  | C | MVP
16 | Make batter trails look better | ie. Mix the trails color up a lil | -
17 | Improve batter spread |  | C
18 | Add dynamic pancake spreed |  | C
19 | Make pancakes cook |  | WIP
20 | Add AI
21
22
23
24
25
26
27
28
29
30

## Todo (Arduino)
Project Sheet - Todo
ID | Task Name | Task Details | Status | Group | Sub Group | Notes
0 | Add Color sencer to detect which pan we are pouring batter into |  | C
1 | Add Wireless commication for jug and whisk |  | -
2 | Sand and pollish cabnit |  | -
3 | Update to unity |  | C
4 | Try ulrasound for jug position |  | C
5 | try IR for just position |  | C
6 | Replace MPU |  | -
7 | Replace Jug Gyro |  | -
8
9
10