## Summary
Project Sheet - Summary
| Project Name | Aly.Cntl.Pancake | Project Type | Alt-Ctrl & Video Game
| Start Date | 2019-06-21 | Target end date | 2019-07-19
| Days To go | 7 | Project Length (days) | 28
| That's | 75% | Of your fucking time used
Progress (All)
| Compleat | 43 | Incompleat | 21 | Total Jobs | 64 | Work in Progress | 1
| % | 67.19% | % | 32.81% | % | 100% | % | 1.562%
| Peak % | 67.19%
Todo
| Task / Todo |  |  |  | Task / Todo
| Not Stated | 16 | 28.57% |  | Not Stated | 4 | 50%
| WIP | 1 | 1.786% |  | WIP | 0 | 0%
| Testing | 0 | 0% |  | Testing | 0 | 0%
| Compleat | 26 | 46.43% |  | Compleat | 4 | 50%
| Removed | 0 | 0% |  | Removed | 0 | 0%
| Fixed | 13 | 23.21% |  | Fixed | 0 | 0%
| Total | 56 | 100% |  | Total | 8 | 100%
| Incompleat Task | 30.36% |  |  | Incompleat Task | 50%
| Compleat Task | 69.64% |  |  | Compleat Task | 50%
Progress Log | [5 empty] | Task Stats |  |  |  |  | Even move fucking task stats
[6 empty] | Task Added | % | Task Compleat | % | Completed / Add ratio | Avg tasks added Per day | Avg Tasks Comp per day | Actual % to now
# | Date | Task Count | Task Compleat | Incompleat tast | % | [8 empty] | Actual % in Week
0 | 2019-06-28 | 42 | 14 | 28 | 33.33% | 42 | 0% | 14 | 0% | 0.33333 | 6 | 2 | 21.88% | 21.88%
1 | 2019-07-05 | 55 | 29 | 26 | 52.73% | 13 | -69.05% | 15 | 7.143% | 1.1538 | 1.8571 | 2.1429 | 45.31% | 23.44%
2 | 2019-07-12 | 64 | 43 | 21 | 67.19% | 9 | -30.77% | 14 | -6.667% | 1.5556 | 1.2857 | 2 | 67.19% | 21.88%
3 | 2019-07-19 | 64 | 43 | 21 | 67.19% | 0 | -100% | 0 | -100% | #DIV/0! | #DIV/0! | #DIV/0! | 67.19% | 0%
4
Formulas:
Aly.Cntl.Pancake = DAYS([Alt-Ctrl & Video Game, row above],NOW())
Alt-Ctrl & Video Game = DAYS([Alt-Ctrl & Video Game, row above],[Aly.Cntl.Pancake, row above])
Even move fucking task stats = IF(NOW()<[Project Name], [Task Stats]/DAYS(NOW(),C4), [Task Stats]/DAYS([Project Name],C4))
Even move fucking task stats = IF(NOW()<[Project Name], [Task Stats]/DAYS(NOW(),[Project Name, row above]), [Task Stats]/DAYS([Project Name],[Project Name, row above]))
Avg Tasks Comp per day = IF(NOW()<[Project Name], [Task Compleat]/DAYS(NOW(),C4), [Task Compleat]/DAYS([Project Name],C4))
Avg Tasks Comp per day = IF(NOW()<[Project Name], [Task Compleat]/DAYS(NOW(),[Project Name, row above]), [Task Compleat]/DAYS([Project Name],[Project Name, row above]))

## Todo (Game Main)
Project Sheet - Todo
ID | Task Name | Task Details | Status | Group | Sub Group | Notes
0 | Translate panMovement (input) to the pancake when in the fryingPan |  | C
1 | Make sure that the pancakes and frying pan are updating correctly | sa in the pan is unset from the pancake and the pancake is unset from the pan when the pancake enters/exits the pan | C |  |  | The pancakes are not being removed from the pancake list in FryingPan_pancake
2 | Add more rays to pancake | Or use a serph ray. Atm it only uses a single ray so in the pan in not inline with the pancake the collision is missed | c
3 | Fixed batter wobble when the jug is in it idle position |  | -
4 | fix batter spread | the first batter ball can be massive for some reason | Fixed |  |  | I think this is caused during the pan changes, if shaky with the jug. Caused by uncalmed precentage :¦
5 | Finish adding pancake states | so each has its own color ect. | C
6 | detect what side of the pancake in face down in the pan |  | C
7 | Add AI |  | -
8 | Add pancake fire |  | C
9 | Add pan smoke |  | C
10 | Add a lil bit of force to the pancake to make shore it comes back to the player. IE a bit of backfroce form the force point |  | - |  |  | ?? Maybe. This seams to of fixed since fixing other bugs
11 | Change distance in PancakeJoint to pancakeJointDistance | in has much beter results and is more consistent | C
12 | Add jug movment from webcam |  | -
13 | Add Mouse/Keyboard inputs |  | -
14 | Add object classes ie. Pancake, fryingpan to store all the main comps of the object so we do need to keep using GetComponent and to make it all lil more clear :) |  | wip
15 | Add extra frection on pancake that on edge of pan |  | c
16 | Add pancake mixture spread, by angle of pan | ie. Deform the shape of the pancake | -
17 | Improve radius algor of pancakes | so the distance from center is dynamic (link id: 16) | - |  |  | This can not be compled until ID 16 is completed
18 | Stop the edges of pancakes spreading throught the pan when mixture | the pancake need to move inwards | C
19 | Fixed Flip not rotating |  | Fixed
20 | flaten pancake when it out of the pan |  | C
21 | blend the pancakes shape when entering the pan |  | -
22 | Level out pancake once below rotate delta thresshold | wtf is this?? Ooooo I remember now. Once the pancake rotation delta drops below a thresshold we need to level the pancake out to the next 180 degrees | C
23 | weight the pancake joints |  | -
24 | Fix TransformToUpforce excepting every value. | it should only except the first and any that are thurther away from the center | Fixed
25 | Add Mass to pancakes |  | c
26 | Fixed pancaked turning into bird like shapes | Ok I belive this is happen cus all the joints at hiting max distance at the same time, I think. So I need to either correct the position befor we update the joints or we need temp update the max distance. TBF I think that correcting the position will be better. but is sounds like a pain | Fixed
27 | Make pancakes slide a lil in the fryingPan :) |  | c
28 | Add destroy pancake |  | C
29 | Fixed Pancake rising up when its position is being corrected |  | Fixed
30 | Fix incorrect flip rotation | the flip rotation need to be alined with its velocity | Fixed
31 | Trigger fire alarm and fire fx |  | C
32 | When pancake go to a fire state the pan should not catch fire untill the other side is at least perfect | So when pan reach burnt state it should slowly cook the other side (say x0.25) and once at fire state x0.5 cook speed ?? | C
33 | pan temp need to be more dynamic |  | C
34 | pancake cook timer need to reset when batter is added to mixture |  | C
35 | Fix stateTimer not updateing with the remaining time from the last state |  | Fixed
36 | Make pancake keep the rotation when they land in the pan | Im think that I might just scale the object negative when fliped, so that will alow this, we shell see… | -
37 | Make fire and smake FX more dynamic | so its more inline with the pancake | -
38 | Fixed spwaning pancakes and faliing through pan instatly | See ID 42, that might fix this. | Fixed |  |  | or 43 might of fixed this
39 | Add pan steam |  | C
40 | Make pan steam dynamic based on pan temp |  | C
41 | Improve the heat up / cool down of pan temp | currently it heats up far to fast. I think it might be worth take some form of conductive value into account | C
42 | Fix pancake force being inverted when on the flip side (side 1 face down) | This is causing the pancake to go fling down streat throught the pan. This might be what is causing (ID 38) since for some resason when it is spwaned it starts on face one. | C
43 | Fix pancakes starting on face 1 rater than face 2. |  | Fixed
44 | Fixed pancake roating in the opersit direction when face one is down |  | Fixed
45 | Fixed pancake be able to flip when in mixture state and sticking when no mixture state | It should be the opersit you tit | Fixed
46 | Fix pancake being scaled by a mixture pancake when the user pours batter onto a pancake that is not mixture | I think I might have to add a new class for this so the already cooked pancake follows the mixture pancake to reprevent it being scaled by the mixture pancake. Also this way is can contiue cooking slowly and it will be easyer to work out if this is the case :D | C
47 | Add air friction for by the angle of the pancake |  | C
48 | Pancake child need to take the contact offset into account when becoming a child of a pancake | and I think mabe batter mixture should push the pancake a lil and the pancake becoming a child should maybe sit in the midle a lil and it needs to remember which side down it was :D | -
49 | Slow down cooking speed if pancake is a child of anouther pancake |  | C
50 | Fix joint position and rotation when fliped :¦ |  | Fixed
51 | Pancake joints need to rotate down when out side the pan |  | -
52 | Pancake rotation when going into the pan, it cant snap in ffs :) |  | -
53 | When entering the pan if the center is outside of the bounds, it needs to not enter the pan |  | -
54 | Fixed Pancake velocity not translating to pan local space |  | -
55 | Fix panposition when the position has been corrected | its causing the pancake to "Stick" to the edges of the pan | Fixed

## Todo (Arduino)
Project Sheet - Todo
ID | Task Name | Task Details | Status | Group | Sub Group | Notes
0 | Add Color sencer to detect which pan we are pouring batter into |  | C
1 | Add Wireless commication for jug and whisk |  | -
2 | Sand and pollish cabnit |  | -
3 | Update to unity |  | C
4 | Try ulrasound for jug position |  | C
5 | try IR for just position |  | C
6 | Replace MPU |  | -
7 | Replace Jug Gyro |  | -
8
9
10

## Working outs
629.3
Gravity | [7 empty] | Gravity | [5 empty] | Gravity |  |  |  | R | 90
9.81 | 0.02 | 0.1962 | [5 empty] | 9.81 | 0.02 | 0.1962 |  |  |  | 9.81 | 0.02 | 0.1962
|  | Translated Vector3 (x, y, z) | [7 empty] | Translated Vector3 (x, y, z) | [5 empty] | Translated Vector3 (x, y, z)
|  | -1.3188 | 7.2 | 2.7385 | [5 empty] | 1.3188 | 7.2 | 2.7385 |  |  |  | 1.49e-07 | 4.6256 | 1.3231
a = | x+z | 1.4197 | [5 empty] | a = | x+z | 2.0286 |  |  |  | a = | x+z | 0.66153
b = | y | 7.2 | [5 empty] | b = | y | 7.2 |  |  |  | b = | y | 4.6256
| rotSpeed | 5.0715 | 912.8779 |  | 18.2576 |  |  |  | rotSpeed | 14.606 | 1314.5399 |  | 26.2908 |  | rotSpeed | 3.06 | 275.3965 |  | 5.5079
[10 empty] | 0.28175 | [5 empty] | 0.14302
[8 empty] | Gravity | [5 empty] | Gravity |  |  |  | R | 90
[8 empty] | 9.81 | 0.02 | 0.1962 |  |  |  | 9.81 | 0.02 | 0.1962
[10 empty] | Translated Vector3 (x, y, z) | [5 empty] | Translated Vector3 (x, y, z)
[10 empty] | 1.3188 | 7.2 | 2.7385 |  |  |  | 1.49e-07 | 4.6256 | 1.3231
[8 empty] | a = | x*z | 3.6114 |  |  |  | a = | x*z | 1.9714e-07
[8 empty] | b = | y | 7.2 |  |  |  | b = | y | 4.6256
[9 empty] | rotSpeed | 26.002 | 2340.1778 |  | 46.8036 |  | rotSpeed | 23463849.4014 | 2111746446.1303 |  | 42234928.9226
[8 empty] | side down | side up
[8 empty] | 0 | 1
1
[6 empty] | angle | mod |  |  | angle | mod
[5 empty] | 0 | 42 | 174 | 42 |  | 132 | 180 | 132 |  | 87 |  |  | 48 |  | 48 | 42
[5 empty] | 140 | 50 | 175 | 50 |  | 140 | 180 | 140 |  | 95 |  |  | 40 |  | 40 | 50
[5 empty] | 148 | 58 | 176 | 58 |  | 148 | 180 | 148 |  | 103 |  |  | 32 |  | 32 | 58
[5 empty] | 156 | 66 | 177 | 66 |  | 156 | 180 | 156 |  | 111 |  |  | 24 |  | 24 | 66
[5 empty] | 164 | 74 | 178 | 74 |  | 164 | 180 | 164 |  | 119 |  |  | 16 |  | 16 | 74
[5 empty] | 172 | 82 | 179 | 82 |  | 172 | 180 | 172 |  | 127 |  |  | 8 |  | 8 | 82
[5 empty] | 180 | 90 | 180 | 90 |  | 180 | 180 | 0 |  | 45 |  |  | 0 |  | 0 | 90
[5 empty] | 188 | 98 | 180 | 98 |  | 188 | 180 | 8 |  | 37 |  |  | -8 |  | 8 | 82
[5 empty] | 196 | 106 | 180 | 106 |  | 196 | 180 | 16 |  | 29 |  |  | -16 |  | 16 | 74
[5 empty] | 204 | 114 | 180 | 114 |  | 204 | 180 | 24 |  | 21 |  |  | -24 |  | 24 | 66
[5 empty] | 212 | 122 | 180 | 122 |  | 212 | 180 | 32 |  | 13 |  |  | -32 |  | 32 | 58
[5 empty] | 220 | 130 | 180 | 130 |  | 220 | 180 | 40 |  | 5 |  |  | -40 |  | 40 | 50
[5 empty] | 228 | 138 | 180 | 138 |  | 228 | 180 | 48 |  | 3 |  |  | -48 |  | 48 | 42
[5 empty] | 236 | 146 | 180 | 146 |  | 236 | 180 | 56 |  | 11 |  |  | -56 |  | 56 | 34
[5 empty] | 244 | 154 | 180 | 154 |  | 244 | 180 | 64 |  | 19 |  |  | -64 |  | 64 | 26
[5 empty] | 252 | 162 | 180 | 162 |  | 252 | 180 | 72 |  | 27 |  |  | -72 |  | 72 | 18
[5 empty] | 260 | 170 | 180 | 170 |  | 260 | 180 | 80 |  | 35 |  |  | -80 |  | 80 | 10
[5 empty] | 268 | 178 | 180 | 178 |  | 268 | 180 | 88 |  | 43 |  |  | -88 |  | 88 | 2
[5 empty] | 276 | 186 | 180 | 6 |  | 96 | 180 | 96 |  | 51 |  |  | 84 |  | 84 | 6
[5 empty] | 284 | 194 | 180 | 14 |  | 104 | 180 | 104 |  | 59 |  |  | 76 |  | 76 | 14